## Sprint1
Week #1 (4 days / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 4*4) | D1 | D2 | D3 | D4
|  |  |  | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20
|  |  |  | 16 | 11 | 6 | 0 | Ideal Burndown
|  |  | 16 | 16 | 13 | 7 | 0 | Remaining Hrs (Total)
Initial SetUP | Research on Tech Stack | Abhiram | 4 | 4 | 4 | 3 | 0
| Review Documents & Understand project requirements | Anuhya | 4 | 4 | 3 | 2 | 0
| Task Allocation | Harsha | 4 | 4 | 3 | 1 | 0
| Scrum set up | Manikanta | 4 | 4 | 3 | 1 | 0
Team:
Abhiram | 4 hours / Week
Anuhya | 4 hours / Week
Harsha | 4 hours / Week
Manikanta | 4 hours / Week
Total Available Hours During Sprint 1: | 16

## Sprint2
Week #2 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 6*4) | D1 | D2 | D3 | D4
|  |  |  | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27
|  |  |  | 24 | 15 | 7 | 0 | Ideal Burndown
|  |  | 24 | 24 | 14 | 10 | 0 | Remaining Hrs (Total)
Initial Set Up | Architecture Diagram | Abhiram | 6 | 6 | 3 | 3 | 0
| Create and update the README.md file | Anuhya | 6 | 6 | 4 | 2 | 0
DB and AWS initial Set Up | Set Up DB and AWS | Harsha | 6 | 6 | 4 | 3 | 0
Set Up Scrum Schedules | Set Up Scrum Meetings, sheets, etc. | Manikanta | 6 | 6 | 3 | 2 | 0
Team:
Abhiram | 6 hours / Week
Anuhya | 6 hours / Week
Harsha | 6 hours / Week
Manikanta | 6 hours / Week
Total Available Hours During Sprint 2: | 24

## Sprint3
Week #3 (4 days / week3)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 8*4) | D1 | D2 | D3 | D4
|  |  |  | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03
|  |  |  | 32 | 21 | 10 | 0 | Ideal Burndown
|  |  | 32 | 30 | 22 | 11 | 0 | Remaining Hrs (Total)
Front End Coding for Components | Initial UI wireframing & Register/Sign-Up UI | Abhiram | 8 | 6 | 6 | 3 | 0
| Booking Page Set Up | Anuhya | 8 | 8 | 5 | 2 | 0
| Home Page Set Up | Harsha | 8 | 8 | 4 | 3 | 0
| Basic Front end set up | Manikanta | 5 | 5 | 4 | 1 | 0
| Scrum Meeting Updates | Manikanta | 3 | 3 | 3 | 2 | 0
Team:
Abhiram | 8 hours / Week
Anuhya | 8 hours / Week
Harsha | 8 hours / Week
Manikanta | 8 hours / Week
Total Available Hours During Sprint 3: | 32

## Sprint4
Week #4 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 8*4) | D1 | D2 | D3 | D4
|  |  |  | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10
|  |  |  | 32 | 22 | 12 | 0 | Ideal Burndown
|  |  | 32 | 32 | 25 | 11 | 0 | Remaining Hrs (Total)
User Account Page, Home Page, Login Page, Sign Up page,Register Page, Booking Page,Confirmation Page | Login UI | Abhiram | 5 | 5 | 3 | 1 | 0
| User Account | Anuhya | 5 | 5 | 3 | 2 | 0
| Home Page | Harsha | 4 | 4 | 4 | 2 | 0
| Login Page,Register Page Setup | Manikanta | 4 | 4 | 3 | 1 | 0
| Backend Setup | Abhiram | 4 | 4 | 4 | 2 | 0
| Booking confirmation and payment page | Anuhya | 4 | 4 | 3 | 2 | 0
| Booking Page Setup | Harsha | 3 | 3 | 3 | 1 | 0
| Resolve UI conflicts between login & register components CSS | Manikanta | 3 | 3 | 2 | 0 | 0
Team:
Abhiram | 8 hours / Week
Anuhya | 8 hours / Week
Harsha | 8 hours / Week
Manikanta | 8 hours / Week
Total Available Hours During Sprint 4: | 32

## Sprint5
Week #5 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 8*4) | D1 | D2 | D3 | D4
|  |  |  | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 34 | 22 | 11 | 0
front end pages | Rooms Page | Abhiram | 5 | 5 | 2 | 2 | 0
| Hotel Dialog | Anuhya | 4 | 4 | 3 | 1 | 0
| Booking Page | Harsha | 4 | 4 | 3 | 1 | 0
| Login Page | Manikanta | 4 | 4 | 3 | 2 | 0
| Dynamic Room Prices | Abhiram | 4 | 6 | 3 | 0 | 0
| Hotel List UI Components | Anuhya | 3 | 3 | 2 | 2 | 0
Backend Set Up and Rating | Backend Set Up | Harsha | 4 | 4 | 3 | 1 | 0
| Checkout Page | Manikanta | 4 | 4 | 3 | 2 | 0
Team:
Abhiram | 8 hours / Week
Anuhya | 8 hours / Week
Harsha | 8 hours / Week
Manikanta | 8 hours / Week
Total Available Hours During Sprint 5: | 32

## Sprint6
Week #6 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 8*4) | D1 | D2 | D3 | D4
|  |  |  | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 21 | 14 | 0
front end pages , Admin Page | Updating Frontend Page | Abhiram | 5 | 5 | 2 | 2 | 0
| Manage Booking Page | Anuhya | 3 | 3 | 3 | 1
Backend APIs for login /sign up, Booking hotel, Resloving Issue in Frontend | API for Bookings | Harsha | 6 | 4 | 3 | 4 | 0
| API for Login | Manikanta | 5 | 5 | 3 | 2 | 0
| Resloving Issue in Frontend | Abhiram | 4 | 4 | 2 | 2 | 0
| API for search hotels | Anuhya | 4 | 4 | 3 | 1 | 0
| Resloving Issue in Frontend | Harsha | 4 | 4 | 2 | 1 | 0
DB Set Up and Connection with API | DB Set Up with API | Manikanta | 3 | 3 | 3 | 1 | 0
Team:
Abhiram | 8 hours / Week
Anuhya | 8 hours / Week
Harsha | 8 hours / Week
Manikanta | 8 hours / Week
Total Available Hours During Sprint 5: | 32

## Sprint7
Week #7 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 8*4) | D1 | D2 | D3 | D4
|  |  |  | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 18 | 12 | 0
Frontend/Backend intergration ,Issue Resloving | Register API | Abhiram | 4 | 4 | 2 | 2 | 0
| Login API integration in frontend | Manikanta | 4 | 4 | 2 | 1 | 0
| Final issue Resloving | Harsha | 8 | 8 | 5 | 3 | 0
| Hotel Search API call integration | Anuhya | 4 | 4 | 2 | 2 | 0
| Frontend/Backend intergration | Abhiram | 6 | 6 | 4 | 2 | 0
Initial Connection with database | DB Set Up | Harsha | 2 | 2 | 0 | 0 | 0
| DB data Population | Anuhya,Manikanta | 2,2 | 4 | 3 | 2 | 0
Team:
Abhiram | 8 hours / Week
Anuhya | 8 hours / Week
Harsha | 8 hours / Week
Manikanta | 8 hours / Week
Total Available Hours During Sprint 7: | 32

## Sprint8
Week #8 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 27 | 12 | 0
Final Integration of APIs with DB, TESTING | Component integration with db and Test own components | Abhiram | 5 | 5 | 5 | 2 | 0
| Component integration with db and Test own components | Anuhya | 8 | 8 | 6 | 3 | 0
| Component integration with db and Test own components | Harsha | 8 | 8 | 6 | 2 | 0
| Component integration with db and Test own components | Manikanta | 8 | 8 | 5 | 4 | 0
AWS SET Up | AWS Set Up | Abhiram | 3 | 3 | 5 | 1 | 0
Team:
Abhiram | 8 hours / Week
Anuhya | 8 hours / Week
Harsha | 8 hours / Week
Manikanta | 8 hours / Week
Total Available Hours During Sprint 8: | 32